## Sheet1
LINDE PRE-DRESSING OF COLUMNS - WORK CHECKLIST
No. | Description | PIC | Start | Finish | Assignment date | Status | Actual finish date | Remark
1 | Mobilisation of Project Management Team | Tuan HN | 2019-12-24 | 2020-01-05 | 2019-12-24
2 | Office preparation | Thai PN | 2019-12-24 | 2020-01-05 | 2019-12-24
3 | Warehouse preparation | Toan DV | 2019-12-24 | 2020-01-10 | 2019-12-24 |  |  | Check packing list
4 | Workshop preparation | Ngoc NT | 2020-01-02 | 2020-01-15 | 2019-12-24
5 | Yard layout & preparation | Ngoc NT | 2020-01-02 | 2020-01-10 | 2019-12-24
6 | Set up Server | Thai PN | 2019-12-24 | 2019-12-30 | 2019-12-24
7 | Transfer document from Bidding team to Execution team | Son TV | 2019-12-25 | 2019-12-30 | 2019-12-24
8 | Project document list (MDR) | Khai BC | 2020-01-02 | 2020-01-08 | 2019-12-24
9 | Project Procedures preparation | Key PMT | 2020-01-02 | 2020-01-20 | 2019-12-24
10 | Project Schedule | Truong VM | 2020-01-02 | 2020-01-07 | 2019-12-24
11 | Submit WPS and Welder to Company | Khai BC | 2019-12-24 | 2020-01-05 | 2019-12-24
12 | WPS & Welder Qualification | Khai BC | 2020-01-02 | 2020-02-20 | 2019-12-24
13 | Test panel | An CX | 2020-01-02 | 2020-01-20 | 2019-12-24
14 | Budget preparation | Key PMT | 2020-01-02 | 2020-01-20 | 2019-12-24
15 | Mobilization direct manpower | Ngoc NT | 2020-01-02 | 2020-01-20 | 2019-12-24
16 | Mobilization equipment and tools | Ngoc NT | 2020-01-02 | 2020-01-20 | 2019-12-24
17 | Order consumable | Ngoc NT | 2019-12-24 | 2019-12-30 | 2019-12-24
18 | Preparation for Signing contract on 08/01/2020 | Anh ND | 2019-12-24 | 2020-01-05 | 2019-12-24
19 | Preparation for Receive of material on 15/01/2020 | Toan DV | 2019-12-24 | 2020-01-10 | 2019-12-24
20 | First cutting preparation 15/02/2020 | Ngoc NT | 2020-01-02 | 2020-02-10 | 2019-12-24
21 | PMS Operation preparation | Nam TB/ Hung NV | 2019-12-24 | 2020-01-05 | 2019-12-24 |  |  | Check item code
22 | Issue shop drawing | Nam TB | 2020-01-02 | 2020-02-15 | 2019-12-24 |  |  | Required client approve or not?
23 | TR for insulation service | Huy NN | 2019-12-25 | 2020-01-12 | 2019-12-24 |  |  | Ms Hương provide PP
24 | TR for EIT support material | Nam TB | 2019-12-25 | 2020-01-12 | 2019-12-24 |  |  | Ms Hương provide PP
25 | Internal KOM Preparation (Execution plan of each department) | Keys PMT | 2019-12-25 | 2020-01-03 | 2019-12-25
Noted:
- Keys PMT including: NGUYỄN HỮU TUẤN, PHAM NAM THAI, NGUYỄN ĐỨC ANH, NGUYỄN THANH NGỌC, VÕ MINH TRƯỜNG, TRẦN BÌNH NAM, TRẦN T. T. HUYỀN, TRẦN HẢI QUÂN, BÙI CAO KHẢI, TẠ VĂN SƠN