## Slide 1
PROJECT OVERVIEW OF
LINDE
PRE-DRESSING OF COLUMNS

## Slide 2: AGENDA
PROJECT INTRODUCTION
1
SCOPE OF WORK
2
PROJECT MILESTONES
3
PROJECT MANAGEMENT TEAM
4
EARLY WORKS
5

## Slide 3
PROJECT INTRODUCTION
1
CONSTRUCTION:
PIPING/ E&I
TOTAL DIA-INCH:
10046.5 DIA
TOTAL INSULATION AREA:
5448 M2
TOTAL PAINTING AREA
1463.2 M2
CLIENT:
LINDE GROUP
PROJECT NAME:
LINDE – PRE-DRESSING
OF COLUMNS
TOTAL PIPING WEIGHT:
199.9 TONS
DURATION:
02/01/2020 – 15/09/2020

## Slide 4
PROJECT INTRODUCTION
1
METHANOL WASH COLUMN
1302T01
96M
COLUMN: 1200M2 – PIPING: 771.2M2
DESCRIPTION
TAG NAME
HEIGHT
INSULATION
13 PCS – 2692 DIA – 703M – 61.5T
PIPING
635M2
PAINTING
20/02/2020
85% MATERIAL

## Slide 5
PROJECT INTRODUCTION
1
HOT REGENERATION COLUMN
1307T04
67M
COLUMN: 660M2 – PIPING: 158.5M2
DESCRIPTION
TAG NAME
HEIGHT
INSULATION
12 PCS – 1182 DIA – 373M – 10.8T
PIPING
122.2M2
PAINTING
20/02/2020
85% MATERIAL

## Slide 6
PROJECT INTRODUCTION
1
METHANOL/ WATER SEPERATION COLUMN
1309T05
39M
COLUMN: 160M2 – PIPING: 29.1M2
DESCRIPTION
TAG NAME
HEIGHT
INSULATION
7 PCS – 351 DIA – 175M – 1.65T
PIPING
23.1M2
PAINTING
20/02/2020
85% MATERIAL

## Slide 7
PROJECT INTRODUCTION
1
SOUR WATER STRIPPER
1206T01
34M
COLUMN: 150M2 – PIPING: 44M2
DESCRIPTION
TAG NAME
HEIGHT
INSULATION
11 PCS – 457 DIA – 191M – 4.2T
PIPING
55.2M2
PAINTING
20/02/2020
85% MATERIAL

## Slide 8
PROJECT INTRODUCTION
1
H2S ENRICHMENT COLUMN INCLUDING CO2 SEPARATOR
1306T03/1304D13
83M
COLUMN: 1150M2 – PIPING: 833.8M2
DESCRIPTION
TAG NAME
HEIGHT
INSULATION
16 PCS – 2981 DIA – 840M – 69.7T
PIPING
507.1M2
PAINTING
20/02/2020
85% MATERIAL

## Slide 9
PROJECT INTRODUCTION
1
SOUR WATER STRIPPER II
1206T11
35M
COLUMN: 190M2 – PIPING: 71.7M2
DESCRIPTION
TAG NAME
HEIGHT
INSULATION
11 PCS – 811 DIA – 269M – 6.2T
PIPING
81.2M2
PAINTING
20/02/2020
85% MATERIAL

## Slide 10
PROJECT INTRODUCTION
1
MINIMUM REQUIRED AREA FOR PRE-DRESSING OF COLUMNS

## Slide 11
SCOPE OF WORK
2
Receive free-issued materials (Piping, E&I) CIF at commercial port
1
Receive Column bodies at PTSC M&C yard follow CIF
2
Pre-fabricate piping, painting (including PWHT, NDT, RT service)
3
4
Installation of piping, valves, Insulation (Include supply insulation materials) for all columns
5
Supply materials, fabrication, installation EIT support materials.
Install cable tray ladder, cable pulling, tubing connection.
Install electrical heat tracing, lighting, junction boxes
6
Preservation, Mechanical Completion and Load-out (FOB) (without sea fastening)

## Slide 12
PROJECT EXECUTION MILESTONES
3
02/01/20
Start mobilization of Project team
15/01/20
First cutting
15/02/20
03/06/20
29/06/20
Start installation work
Mechanical Completion
Start insulation work and EIT
15/09/20
(LD)
Start receiving materials free issue by Company
Open file

## Slide 13
LEAD CONST.
ENGINEERING
TRẦN BÌNH NAM
PROCUREMENT
MANAGER
TRẦN T. T. HUYỀN
DOCUMENT CONTROLLER
TẠ VĂN SƠN
E&I
INSPECTOR
TBA
STR/PIP/MEC
INSPECTOR
TBA
PIPING CE
TBA
EIT CE
TBA
LIFTING CE
TBA
MATERIAL
CONTROLLER
ĐẶNG VĂN TOÀN
PROJECT MANAGEMENT TEAM (SUBMITTED)
4
PROJECT MANAGER
NGUYỄN HỮU TUẤN
PROJECT COORDINATOR
PHAM NAM THAI
PROJECT DIRECTOR
NGUYỄN DƯƠNG LÂM
NGUYỄN ĐỨC ANH
ĐOÀN QUỐC DŨNG – CONTRACT ENGINEER
PLANNING
MANAGER
VÕ MINH TRƯỜNG
CONSTRUCTION
MANAGER
NGUYỄN THANH NGỌC
E&I SUP.
ĐINH QUỐC ÂN
STR/PIP/MEC SUP.
NGUYỄN KHẮC TRỌNG
CHU XUÂN AN
PAINTING/
SCAFFOLD SUP.
QC MANAGER
BÙI CAO KHẢI
PRODUCTION
CONTROL LEADER
TRẦN KHÁNG
LEAD HSE OFFICER
TRẦN HẢI QUÂN
PROJECT CONTROL
MANAGER

## Slide 14
EARLY WORKS
5
1
Final PMT submission
2
Preparation for Office, Warehouse and Fabrication workshop
3
Develop Project Schedule
4
Project Procedures preparation
6
WPS & Welder Qualification, Test panel
7
Order consumables
8
Issue shop drawing
9
Mobilization equipment and tools
10
Mobilization direct manpower
Budget preparation
5
Open link