|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| From: PTSC M&C | | To: | | PTSC M&C |
| Discipline(s): | PROJECT MANAGEMENT TEAM | | | |
| Date / Time: | 06-Jan-2020 @ 09:30 to 11:00 AM | | | |
| Place of meeting: | PTSC M&C Room B02-OF3.02 | | | |
| Minute by: | Pham Nam Thai | |  | |
| **Subject:** | **Project Weekly Meeting** | | | |

|  |  |  |
| --- | --- | --- |
| **Attendees** | | |
| **Name** | **Title** | **Entity** |
| Nguyen Huu Tuan | Project Manager | PTSC M&C |
| Pham Nam Thai | Project Coordinator | PTSC M&C |
| Nguyen Thanh Ngoc | Construction Manager | PTSC M&C |
| Nguyen Huy Tuan | QC Manager | PTSC M&C |
| Nguyen Duc Anh | Project Control Manager | PTSC M&C |
| Vo Minh Truong | Planning Manager | PTSC M&C |
| Tran Thi Thanh Huyen | Procurement Coordinator | PTSC M&C |
| Tran Binh Nam | Construction Engineering Lead | PTSC M&C |
| Tran Hai Quan | HSE Manager | PTSC M&C |
| Doan Quoc Dung | Contract Engineer | PTSC M&C |
| Chu Xuan An | Painting/ Scaffolding Supervisor | PTSC M&C |
| Dang Van Toan | Material Controller | PTSC M&C |
| **Distribution List** | | |
| **Name** | **Title** | **Entity** |
| Nguyen Duong Lam | Project Director | PTSC M&C |
|  |  |  |

|  |  |  |
| --- | --- | --- |
| **Name** | **Date** | **Signature** |
| Nguyen Huu Tuan | 06-Jan-2019 |  |
|  |  |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | **Subject** | **Action** | **Status** | **Due Date** |
| I | **GENERAL** |  |  |  |
|  | **PMT** |  |  |  |
|  | PMT submission for approval | NH Tuan |  |  |
|  | Finalize Office layout and mobilization   * Office is under completion. | NH Tuan/  PN Thai |  | 05/01/2020 |
|  | Document control, template, no. request, …   * Already sent TC to COMPANY | TV Sơn |  | ~~30/12/2019~~  06/01/2020 |
|  | Budget preparation for all Departments   * Received E&I, Painting/ Scaffolding, Structure * Waiting for budge: Piping, EG WS | Key PMT |  | ~~20/01/2020~~  10/01/2020 |
|  | Internal KOM Preparation - Each team (department) are requested to present the plan and execution.   * Final KOM 14/01 * 1st draft 10/01 * Agenda 06/01 | Key PMT |  | ~~03/01/2020~~  14/01/2020 |
|  | Prepare MDR Project   * Received QC, HSE feedback * Define critical document list | TV Son |  | 06/01/2020 |
|  | Prepare CE MDR + AFC Received   * Send on 06/01 | TB Nam |  | 15/01/2020 |
|  | Project Executing Plan   * Sent to Disciplines to input * Waiting for feedback not later than 07/01/2020 | PN Thai |  | 12/01/2020 |
| II | **HSE** |  |  |  |
|  | Prepare HSE Plan | TH Quan |  | 18/01/2020 |
| III | **PROJECT CONTROL** |  |  |  |
|  | Check Construction allowance following TC during bidding | ND Anh | Closed | 08/01/2020 |
|  | Check CMS (from Linde) application and operation   * CMS is required, training will be provided from COMPANY * WSD is also required | PN Thai/  ND Anh |  | 08/01/2020 |
|  | Check packing list information from Linde   * Already sent TC to COMPANY | PN Thai/  ND Anh |  | 08/01/2020 |
|  | Preparation for Signing contract on 08/01/2020 | ND Anh |  | 05/01/2020 |
|  | Prepare Performance Bond | ND Anh |  | 18/01/2020 |
|  | Prepare Insurance Cover   * Issued RFQ | ND Anh |  | 18/01/2020 |
| IV | **PLANNING** |  |  |  |
|  | Prepare project schedule   * 1st draft 06/01 | VM Truong/ NV Thong |  | 07/01/2020 |
|  | Preparation for Receive of material on 15/01/2020 | DV Toàn |  | 10/01/2020 |
|  | Warehouse preparation   * Submitted request * Yard 2000m: provided * Pending covered warehouse | DV Toàn/ NT Ngoc | submitted | 10/01/2020 |
|  | Detailed-90-DAY-Mobilisation Schedule   * Already sent to disciplines for review * To finalize schedule on 10/01 | VM Truong |  | 18/01/2020 |
| V | **QA/QC** |  |  |  |
|  | Submit WPS and Welder to Company   * To submit 07/01 | N Huy Tuan |  | 05/01/2020 |
|  | WPS & Welder New Qualification   * Propose solution including in Procedure 15/01 | N Huy Tuan |  | 15/02/2020 |
|  | Test panel   * TR for painting 10/01 | CX AN |  | ~~20/01/2020~~  10/02/2020 |
|  | Prepare ITP for CA/ Client involve | N Huy Tuan |  | 15/01/2020 |
|  | Prepare TR for NDE   * Already sent to Ms Huyen 04/01/2020 * Request for NDE service 07/01 | N Huy Tuan |  | 10/01/2020 |
|  | As-Built Documentation including Quality Records/ Documentation | N Huy Tuan |  | monitor |
| VII | **PROCUREMENT** |  |  |  |
|  | Procurement to develop Procurement plan for disciplines to follow   * To send for review 07/01 | TTT Huyen |  | TBA |
|  | CE Team to input package list (materials/ services) for CE/ DE packages   * Done | TB Nam | Closed | 31/12/2019 |
|  | DE Team to input package list (materials/ services) for DE packages   * Done | NN Huy | Closed | 31/12/2019 |
|  | Construction team input package list for Construction services/ pressure testing   * Done | NT Ngoc | Closed | 31/12/2019 |
|  | QC Team input package list for QC services   * Done | N Huy Tuan | Closed | 31/12/2019 |
| VIII | **CONSTRUCTION ENGINEERING** |  |  |  |
|  | MTO for Piping to be finalized   * TB Nam to distribute to all disciplines | TB Nam/ TLA Minh |  | ~~10/01/2020~~  10/02/2020 |
|  | MTO for E&I to be finalized | TB Nam/TLA Minh |  | ~~10/01/2020~~  10/02/2020 |
|  | Check if drawings require Client approval   * D Anh propose solution to CPY | ND Anh/  TB Nam |  | 08/01/2020 |
|  | TR for E&I Support | TB Nam/TLA Minh |  | 12/01/2020 |
|  | PMS Operation preparation   * Already held meeting and setup Project/ Facility | Nam TB/Hung NV |  | 05/01/2020 |
|  | Issue shop drawing | TB Nam |  | ~~15/02/2020~~  01/02/2020 |
|  | TR for Piping/ Flange/ Bolt nuts/ Fitting/ Gasket | TB Nam/ NV Chung |  | 12/01/2020 |
|  | TR for E&I Miscellaneous | TB Nam |  | 12/01/2020 |
|  | TR for Rolling service | TB Nam |  | 12/01/2020 |
|  | TR for Galvanizing service | TB Nam |  | 12/01/2020 |
|  | TR for Load-out service | TB Nam/ NM Duc |  | 10/01/2020 |
|  | Develop construction sequence | TB Nam/ NT Ngoc |  | 10/01/2020 |
|  | TR for Insulation block | VV Toan/ TB Nam |  | 12/01/2020 |
|  | TR for Insulation Piping & Column | TB Nam | Closed | 12/01/2020 |
|  | TR for materials for packing ship-loose items | TB Nam |  | 12/01/2020 |
| IX | **CONSTRUCTION** |  |  |  |
|  | First cutting preparation 15/02/2020 | NT Ngoc |  | 10/02/2020 |
|  | Prepare for yard layout, workshop   * Waiting for approval | NT Ngoc |  | 15/01/2020 |
|  | Mobilization plan for direct manpower   * Manpower input form from Planning 06/01 | NT Ngoc |  | 20/01/2020 |
|  | Mobilization plan for equipment and tools   * To include in Construction budget | NT Ngoc | Delete | 20/01/2020 |
|  | Budget of Construction (Tools/ Equipment/ Consumables) | NT Ngoc |  | ~~30/12/2019~~  15/01/2019 |
|  | TC for painting for pipe support:  Clarify primer, touch up painting code by Vendor |  |  |  |
| X | **SERVICES/ SUB-CONTRACTOR** |  |  |  |
|  | Nil. |  |  |  |
| XI | **INTERFACES** |  |  |  |
|  | Nil. |  |  |  |
| XII | **AOB** |  |  |  |
|  | Nil |  |  |  |